## Sheet1
https://hul-hub.atlassian.net/browse/V4-553 | Migration (DB Schema) (Muzammil, Shakir Both)
https://hul-hub.atlassian.net/browse/V4-554 | 2- Front End (Admin, User) (User - 29 May 2023 EOD, Admin - 30 May 2023 EOD) (Shakir)
https://hul-hub.atlassian.net/browse/V4-555 | 3- Authentication Module (30 May 2023 => EOD) (Muzammil)
https://hul-hub.atlassian.net/browse/V4-556 | 4- Packages Module (30 May 2023 => EOD) (Shakir)
https://hul-hub.atlassian.net/browse/V4-557 | 5- Purchase Package (User can purchase package) (31 May 2023 => EOD) (Shakir)
https://hul-hub.atlassian.net/browse/V4-558 | 6- Payment Gateway Integration (Paypal/ Stripe) (5 June 2023 => EOD) (Shakir)
https://hul-hub.atlassian.net/browse/V4-559 | 7- Payment History (6 June 2023 => EOD) (Shakir)
https://hul-hub.atlassian.net/browse/V4-560 | 8- Autobot API Integration (5 June 2023 => EOD) (Muzammil)
https://hul-hub.atlassian.net/browse/V4-561 | 9- User Management (Active/ Inactive ¦ Guard Login) (6 June 2023 => EOD) (Muzammil)
https://hul-hub.atlassian.net/browse/V4-562 | 10- Reporting Module (Autobot API History, User History, Wallet History, Dashboard) (9 June 2023 => EOD) (Muzammil, Shakir Both)
https://hul-hub.atlassian.net/browse/V4-563 | 11- End User API Documentation (12 June 2023 => EOD) (Muzammil, Shakir Both)